## Supplemental Feeding-As of June
ACCOMPLISHMENT REPORT
RE: Supplementary Feeding Program (3rd Cycle)
As of June2014
Region | Physical Accomplishment | [11 empty] | Fund Obligations | [29 empty] | Remarks
| Target per WFP |  |  | Adjusted Target |  |  | Total Served | [5 empty] | Amount Allocated to LGUs (Grants) | Fund Obligated | Funds Spent for the Rice and Utensils c/o FO | % | Rate of Accomplishment | Rank | MOA with LGUs | Fund Transfer | Procurement of Utensils |  |  |  | Ranking |  | Nutritional Status | [12 empty] | % of Increase for Normal Status | % of Decrease for Underweight | % of Decrease for Overweight
| LGUs | DCCs | Children | LGUs | DCCs | Children | LGUs | DCCs | Children |  |  | % | [14 empty] | Number of Children Weighed | Nutritional Status before the start of Feeding | [5 empty] | Nutritional Status at the latest
[10 empty] | Cost* | [17 empty] | # DCCh with/Normal Status | % | # Underweight Ch | % | # Overweight | % | # DCCh with/Normal Status | % | # Underweight Ch | % | # Overweight | %
I | 125 | 3282 | 73154 | - | 0 | 88690 | 0 | 3445 | 89724 | 9479850 | 0 | 122.6508 | 117259000 | 130549040 | 15335365 | 111.3339 | 111.3339 | 4 | 125 | 125 | 125 | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 1 | 1 | 3 | 1 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
II | 93 | 2615 | 67391 | 0 | 385 | 43650 | 0 | 2637 | 75624 | 25254400 | 0 | 112.2168 | 107704000 | 111732044 | 0 | 103.7399 | 103.7399 | 1 | 93 | 93 | 87 | partial delivery of utensils done | 2 | 2 | 4 | 2 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
III | 130 | 3905 | 139980 | - | 0 | 4390 | 0 | 2723 | 162769 |  | 0 | 116.2802 | 222422000 | 228449887 | 0 | 102.7101 | 102.7101 | 1 | 128 | 128 |  | 2 LGUs to start this week while 3 LGUs with previous unliquidated funds (past projects) | 3 | 3 | 6 | 3 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2 LGUs (Dipaculao, Aurora & Mexico, Pampanga declined Sy 2012-2013 implementation
IV-A | 142 | 4619 | 165345 | 0 | 3507 | 159883 | 0 | 2613 | 141372 |  | 0 | 85.5012 | 262671000 | 252688800 | 62884272.54 | 96.1997 | 96.1997 | 8 | 141 | 102 |  | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 4 | 4 | 15 | 4 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
IV-B | 72 | 2860 | 84221 | 0 | 2652 | 83770 | 0 | 2509 | 82623 |  | 0 | 98.1026 | 134039000 | 139638900 | 15915065 | 104.1778 | 104.1778 | 4 | 72 | 72 |  | partial delivery of utensils done | 5 | 5 | 16 | 5 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
V | 114 | 4294 | 142480 |  | 0 | 0 | 0 | 3741 | 123791 |  | 0 | 86.8831 | 226182000 | 208016640 | 0 | 91.9687 | 91.9687 | 2 | 93 | 93 |  | 3 LGUs to start this week while 3 LGUs with previous unliquidated funds (past projects) | 6 | 6 | 12 | 6 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 30 LGUs will not implement SY 2012-2013 feeding
VI | 133 | 5557 | 180335 |  | 122 | 4556 | 133 | 5557 | 180335 |  | 0 | 100 | 286097000 | 281322600 | 51326712 | 98.3312 | 98.3312 | 1 | 133 | 133 | 133 | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 7 | 7 | 5 | 7 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
VII | 132 | 4173 | 139271 | 0 | 4582 | 153546 | 0 | 4154 | 145662 |  | 0 | 104.5889 | 221323000 | 224167200 | 40835700 | 101.2851 | 101.2851 | 6 | 132 | 132 |  | partial delivery of utensils done | 8 | 8 | 1 | 8 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
VIII | 143 | 4032 | 106209 | - | 0 | 0 | 0 | 442 | 13469 |  | 0 | 12.6816 | 169769000 | 19611000 | 0 | 11.5516 | 11.5516 | 9 | 133 | 133 | 133 | 4 LGUs to start this week while 3 LGUs with previous unliquidated funds (past projects) | 9 | 9 | 2 | 9 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
IX | 72 | 2577 | 87876 | 0 | 2317 | 103982 | 0 | 0 | 105088 | 23383862.5 | 0 | 119.5867 | 139770000 | 156028835.23 | 0 | 111.6326 | 111.6326 | 1 | 72 | 72 |  | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 10 | 10 | 13 | 10 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
X | 93 | 3110 | 107906 | - | 3249 | 108547 |  |  | 120270 |  | 0 | 111.4581 | 171184000 | 169333320 | 0 | 98.9189 | 98.9189 | 1 | 92 | 92 |  | partial delivery of utensils done | 11 | 11 | 9 | 11 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
XI | 49 | 2515 | 84944 | 0 | 2650 | 97975 | 0 | 1974 | 84645 |  | 0 | 99.648 | 135176000 | 101574000 | 0 | 75.142 | 75.142 | 3 | 49 | 49 | 46 | 5 LGUs to start this week while 3 LGUs with previous unliquidated funds (past projects) | 12 | 12 | 11 | 12 | 10131 | 7704 | 76.0438 | 1773 | 17.5007 | 31 | 0.30599 | 8654 | 85.421 | 814 | 8.0347 | 64 | 0.63172 | 12.3313 | -54.0891 | 106.4516
XII | 50 | 2757 | 93440 | - | 2875 | 93738 | 0 | 2702 | 94515 |  | 0 | 101.1505 | 149416000 | 141712788 | 0 | 94.8445 | 94.8445 | 1 | 50 | 50 | 50 | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 13 | 13 | 10 | 13 | 93567 | 71038 | 75.9221 | 19913 | 21.2821 |  | 0 | 78973 | 84.4026 | 11720 | 12.5258 |  | 0 | 11.1701 | -41.144 | #DIV/0!
NCR | 17 | 1920 | 143002 | - | 2008 | 154876 | 0 | 2088 | 159756 |  | 0 | 111.7159 | 225450000 | 208256161.3 | 0 | 92.3735 | 92.3735 | 7 | 17 | 17 | 17 | partial delivery of utensils done | 14 | 14 | 7 | 14 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
CAR | 77 | 2019 | 43688 | - | 1867 | 40697 | 0 | 950 | 44748 |  | 0 | 102.4263 | 70262000 | 56576576 | 0 | 80.5223 | 80.5223 | 1 | 77 | 67 | 1 | 6 LGUs to start this week while 3 LGUs with previous unliquidated funds (past projects) | 15 | 15 | 14 | 15 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
CARAGA | 73 | 1920 | 64238 | 0 | 2025 | 67990 | 0 | 2025 | 68452 |  | 0 | 106.56 | 103315000 | 106064400 | 0 | 102.6612 | 102.6612 | 1 | 71 | 69 |  | procurement of food commodities still on process in some LGUs; upland communities road not yet accessible for the delivery of food commodities | 16 | 16 | 8 | 16 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
ARMM | 115 | 1340 | 54794 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 88524000 | 0 | 10461900 | 0 | 0 | 5 | 42 | 42 |  | partial delivery of utensils done | 17 | 17 | 12 | 17 |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Ongoing downloading of 2nd tranche to MSWDOs
Total | 1630 | 53495 | 1778274 | 0 | 28239 | 1206290 | 133 | 37560 | 1692843 | 58118112.5 | 0 | 95.1958 | 2830563000 | 2535722191.53 | 196759014.54 | 89.5837 | 96.5349 |  | #REF! | #REF! | #REF! | [7 empty] | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Prepared by: | [7 empty] | Reviewed by: |  |  |  |  | Noted by: | Concured by:
Signed | [7 empty] | Signed | [5 empty] | Signed
Jeffrey R. Tenorio | [7 empty] | Irish M. Opeña |  |  |  |  | Jesusa A. Cabilao | Dir. Margarita V. Sampang, CESO III
AA II | [7 empty] | SFP - Focal Person SWO IV |  |  |  |  | CBWDPD - Division Chief | PSB - Director